## Template
Please note the | A "Small" (S) task: On average, can be completed in less than 1 day | 1
following definitions. | A "Medium" (M) task:Needs the whole time between two daily scrums (give or take) | 2
Most of your tasks should be S or M | A "Large" (L) task: Needs about a week | 4 | [21 empty] | Use these to verify that your numbers add up for each US
[7 empty] | Matthew |  |  |  | Michael |  |  |  | Haylie |  |  |  | Kenzie
User story (US) # | US name | Was US accepted in Sprint 2? | TOTAL Number of tasks ATTEMPTED during Sprint 2 |  | TOTAL Number of tasks COMPLETED during Sprint 2 |  | Number of tasks ATTEMPTED |  | Number of tasks COMPLETED |  | Number of tasks ATTEMPTED |  | Number of tasks COMPLETED |  | Number of tasks ATTEMPTED |  | Number of tasks COMPLETED |  | Number of tasks ATTEMPTED |  | Number of tasks COMPLETED |  |  | ATTEMPTED CHECKSUM | COMPLETED CHECKSUM
US#9 | Edit an item on product backlog | yes | # S tasks | 4 | # S tasks | 4 | # S tasks | 4 | # S tasks | 4 | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | S | PASSED | PASSED
|  |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | M | PASSED | PASSED
|  |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | L | PASSED | PASSED
US#10 | Move an item from product backlog to sprint backlog | yes | # S tasks | 3 | # S tasks | 3 | # S tasks | 1.84 | # S tasks | 1.84 | # S tasks | 0.83 | # S tasks | 0.83 | # S tasks |  | # S tasks |  | # S tasks | 0.33 | # S tasks | 0.33 | S | PASSED | PASSED
|  |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | M | PASSED | PASSED
|  |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | M | PASSED | PASSED
User story (US) # | US name | Was US accepted in Sprint 2? | TOTAL Number of tasks ATTEMPTED during Sprint 2 |  | TOTAL Number of tasks COMPLETED during Sprint 2 |  | Number of tasks ATTEMPTED |  | Number of tasks COMPLETED |  | Number of tasks ATTEMPTED |  | Number of tasks COMPLETED |  | Number of tasks ATTEMPTED |  | Number of tasks COMPLETED |  | Number of tasks ATTEMPTED |  | Number of tasks COMPLETED |  |  | ATTEMPTED CHECKSUM | COMPLETED CHECKSUM
US#11 | Support roles : product owner or team member | no | # S tasks | 5 | # S tasks | 5 | # S tasks | 5 | # S tasks | 5 | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | S | PASSED | PASSED
|  |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | M | PASSED | PASSED
|  |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | L | PASSED | PASSED
US#12 | Accept or reject invitations | yes | # S tasks | 3 | # S tasks | 3 | # S tasks | 3 | # S tasks | 3 | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | S | PASSED | PASSED
|  |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | M | PASSED | PASSED
|  |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | L | PASSED | PASSED
US#13 | View project invitations | yes | # S tasks | 3 | # S tasks | 3 | # S tasks | 3 | # S tasks | 3 | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | S | PASSED | PASSED
|  |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | M | PASSED | PASSED
|  |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | L | PASSED | PASSED
US#14 | Create a task | yes | # S tasks | 2 | # S tasks | 2 | # S tasks | 0.83 | # S tasks | 0.83 | # S tasks | 0.84 | # S tasks | 0.84 | # S tasks | 0.33 | # S tasks | 0.33 | # S tasks |  | # S tasks |  | S | PASSED | PASSED
|  |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | M | PASSED | PASSED
|  |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | L | PASSED | PASSED
US#15 | Edit a task | no | # S tasks | 3 | # S tasks | 3 | # S tasks | 1.5 | # S tasks | 1.5 | # S tasks | 1.5 | # S tasks | 1.5 | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | S | PASSED | PASSED
|  |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | M | PASSED | PASSED
|  |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | L | PASSED | PASSED
US#16 | Move a task from ToDo to Doing | yes | # S tasks | 3 | # S tasks | 3 | # S tasks | 3 | # S tasks | 3 | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | S | PASSED | PASSED
|  |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | M | PASSED | PASSED
|  |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | L | PASSED | PASSED
US#17 | Move a task from Doing to Done | yes | # S tasks | 1 | # S tasks | 1 | # S tasks | 1 | # S tasks | 1 | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | S | PASSED | PASSED
|  |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | M | PASSED | PASSED
|  |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | L | PASSED | PASSED
US#18 | Delete a task | yes | # S tasks | 3 | # S tasks | 3 | # S tasks | 2.5 | # S tasks | 2.5 | # S tasks | 0.5 | # S tasks | 0.5 | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | S | PASSED | PASSED
|  |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | M | PASSED | PASSED
|  |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | L | PASSED | PASSED
US#19 | See progress for a given user story | yes | # S tasks | 3 | # S tasks | 3 | # S tasks | 3 | # S tasks | 3 | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | S | PASSED | PASSED
|  |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | M | PASSED | PASSED
|  |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | L | PASSED | PASSED
US#20 | Accept or reject user stories | no | # S tasks | 3 | # S tasks | 3 | # S tasks | 3 | # S tasks | 3 | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | S | PASSED | PASSED
|  |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | M | PASSED | PASSED
|  |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | L | PASSED | PASSED
US#21 | Create a new sprint board | yes | # S tasks | 3 | # S tasks | 3 | # S tasks | 3 | # S tasks | 3 | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | S | PASSED | PASSED
|  |  | # M tasks | 1 | # M tasks | 1 | # M tasks | 0.5 | # M tasks | 0.5 | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks | 0.5 | # M tasks | 0.5 | M | PASSED | PASSED
| (styling for entire site, Michael's responsibility) |  | # L tasks | 1 | # L tasks | 1 | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks | 1 | # L tasks | 1 | # L tasks |  | # L tasks |  | L | PASSED | PASSED
US#22 | Save scrum board | yes | # S tasks | 3 | # S tasks | 3 | # S tasks | 3 | # S tasks | 3 | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | S | PASSED | PASSED
|  |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | M | PASSED | PASSED
| (parrot logo, original work by Haylie) |  | # L tasks | 1 | # L tasks | 1 | # L tasks |  | # L tasks |  | # L tasks | 1 | # L tasks | 1 | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | L | PASSED | PASSED
US#23 | Load a saved scrum board | yes | # S tasks | 4 | # S tasks | 4 | # S tasks | 4 | # S tasks | 4 | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | S | PASSED | PASSED
|  |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | M | PASSED | PASSED
|  |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | L | PASSED | PASSED
US#24 | View breakdown of work done by each member | yes | # S tasks | 4 | # S tasks | 4 | # S tasks | 4 | # S tasks | 4 | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | S | PASSED | PASSED
|  |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | M | PASSED | PASSED
|  |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | L | PASSED | PASSED
US#25 | Send private messages | no | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | S | PASSED | PASSED
|  |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | M | PASSED | PASSED
|  |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | L | PASSED | PASSED
noo
US#26 | View history of messages sent and received | no | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | # S tasks |  | S | PASSED | PASSED
|  |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | # M tasks |  | M | PASSED | PASSED
|  |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | # L tasks |  | L | PASSED | PASSED